## PPVC_ACT
Activity Level 1 | Activity Level 2 | Activity Level 3 | Activity Level 4 | Zone | Sub Zone | Block | Part | Level | Unit | Module | Actual Start Date | Actual Completion Date | Remarks
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 8 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 8 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 8 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 8 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 9 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 9 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 10 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 10 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 10 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 11 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 11 | M5
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 12 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 13 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 13 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 28 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 28 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 28 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 28 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 8 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 8 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 8 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 8 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 9 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 9 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 10 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 10 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 10 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 11 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 11 | M5
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 12 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 13 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 13 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 27 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 27 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 27 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 27 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 8 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 8 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 8 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 8 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 9 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 9 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 10 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 10 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 10 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 11 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 11 | M5
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 12 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 13 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 13 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 26 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 26 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 26 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 26 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 8 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 8 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 8 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 8 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 9 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 9 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 10 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 10 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 10 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 11 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 11 | M5
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 12 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 13 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 13 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 25 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 25 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 25 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 25 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 8 | M1 |  | 2025-03-08
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 8 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 8 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 8 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 9 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 9 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 10 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 10 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 10 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 11 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 11 | M5
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 12 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 13 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 13 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 24 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 24 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 24 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 24 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 8 | M1 |  | 2025-03-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 8 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 8 | M3 |  | 2025-03-08
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 8 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 9 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 9 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 10 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 10 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 10 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 11 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 11 | M5
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 12 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 13 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 13 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 23 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 23 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 23 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 23 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 8 | M1 |  | 2025-03-03
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 8 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 8 | M3 |  | 2025-03-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 8 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 9 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 9 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 10 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 10 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 10 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 11 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 11 | M5
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 12 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 13 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 13 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 22 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 22 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 22 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 22 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 8 | M1 |  | 2025-02-28
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 8 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 8 | M3 |  | 2025-03-01
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 8 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 9 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 9 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 10 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 10 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 10 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 11 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 11 | M5 |  | 2025-03-08
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 12 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 13 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 13 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 21 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 21 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 21 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 21 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 8 | M1 |  | 2025-02-24
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 8 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 8 | M3 |  | 2025-02-27
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 8 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 9 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 9 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 10 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 10 | M2 |  | 2025-03-08
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 10 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 11 | M1 |  | 2025-03-01
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 11 | M5 |  | 2025-03-06
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 12 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 13 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 13 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 20 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 20 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 20 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 20 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 8 | M1 |  | 2025-02-21
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 8 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 8 | M3 |  | 2025-02-25
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 8 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 9 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 9 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 10 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 10 | M2 |  | 2025-03-06
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 10 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 11 | M1 |  | 2025-02-27
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 11 | M5 |  | 2025-03-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 12 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 13 | M1 |  | 2025-02-21
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 13 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 19 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 19 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 19 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 19 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 8 | M1 |  | 2025-02-19
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 8 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 8 | M3 |  | 2025-02-22
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 8 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 9 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 9 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 10 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 10 | M2 |  | 2025-03-04
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 10 | M4 |  | 2025-02-22
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 11 | M1 |  | 2025-02-25
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 11 | M5 |  | 2025-03-03
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 12 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 13 | M1 |  | 2025-02-19
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 13 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 18 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 18 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 18 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 18 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 8 | M1 |  | 2025-02-15
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 8 | M2 |  | 2025-03-03
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 8 | M3 |  | 2025-02-20
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 8 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 9 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 9 | M3 |  | 2025-02-21
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 10 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 10 | M2 |  | 2025-03-01
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 10 | M4 |  | 2025-02-20
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 11 | M1 |  | 2025-02-22
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 11 | M5 |  | 2025-02-28
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 12 | M3 |  | 2025-03-08
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 13 | M1 |  | 2025-02-26
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 13 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 17 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 17 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 17 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 17 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 8 | M1 |  | 2025-02-12
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 8 | M2 |  | 2025-02-28
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 8 | M3 |  | 2025-02-18
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 8 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 9 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 9 | M3 |  | 2025-02-19
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 10 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 10 | M2 |  | 2025-02-27
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 10 | M4 |  | 2025-02-18
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 11 | M1 |  | 2025-02-20
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 11 | M5 |  | 2025-02-26
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 12 | M3 |  | 2025-03-06
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 13 | M1 |  | 2025-02-24
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 13 | M3 |  | 2025-03-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 16 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 16 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 16 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 16 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 8 | M1 |  | 2025-02-10
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 8 | M2 |  | 2025-02-25
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 8 | M3 |  | 2025-02-15
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 8 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 9 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 9 | M3 |  | 2025-02-17
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 10 | M1 |  | 2025-03-07
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 10 | M2 |  | 2025-02-25
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 10 | M4 |  | 2025-02-15
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 11 | M1 |  | 2025-02-18
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 11 | M5 |  | 2025-02-24
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 12 | M3 |  | 2025-03-04
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 13 | M1 |  | 2025-02-17
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 13 | M3 |  | 2025-03-03
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 15 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 15 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 15 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 15 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 8 | M1 |  | 2025-02-07
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 8 | M2 |  | 2025-02-22
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 8 | M3 |  | 2025-02-12
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 8 | M4 |  | 2025-03-07
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 9 | M1 |  | 2025-03-08
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 9 | M3 |  | 2025-02-13
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 10 | M1 |  | 2025-03-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 10 | M2 |  | 2025-02-21
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 10 | M4 |  | 2025-02-13
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 11 | M1 |  | 2025-02-15
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 11 | M2 |  | 2025-03-07
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 11 | M3 |  | 2025-03-06
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 11 | M5 |  | 2025-02-21
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 12 | M3 |  | 2025-02-28
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 13 | M1 |  | 2025-02-14
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 13 | M3 |  | 2025-02-28
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 14 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 14 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 14 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 14 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 8 | M1 |  | 2025-02-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 8 | M2 |  | 2025-02-20
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 8 | M3 |  | 2025-02-06
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 8 | M4 |  | 2025-03-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 9 | M1 |  | 2025-03-06
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 9 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 9 | M3 |  | 2025-02-11
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 10 | M1 |  | 2025-03-03
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 10 | M2 |  | 2025-02-19
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 10 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 10 | M4 |  | 2025-02-11
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 11 | M1 |  | 2025-02-13
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 11 | M2 |  | 2025-03-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 11 | M3 |  | 2025-03-04
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 11 | M5 |  | 2025-02-19
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 12 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 12 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 12 | M3 |  | 2025-02-27
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 13 | M1 |  | 2025-02-12
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 13 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 13 | M3 |  | 2025-02-26
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 13 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 13 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 13 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 13 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 8 | M1 |  | 2024-11-22
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 8 | M2 |  | 2024-12-23
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 8 | M3 |  | 2024-11-27
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 8 | M4 |  | 2025-03-03
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 9 | M1 |  | 2025-01-15
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 9 | M2 |  | 2024-12-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 9 | M3 |  | 2024-12-04
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 10 | M1 |  | 2025-01-17
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 10 | M2 |  | 2024-12-12
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 10 | M3 |  | 2024-12-31
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 10 | M4 |  | 2025-02-08
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 11 | M1 |  | 2025-02-11
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 11 | M2 |  | 2025-03-03
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 11 | M3 |  | 2024-12-21
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 11 | M4 |  | 2025-03-07
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 11 | M5 |  | 2025-02-17
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 12 | M1 |  | 2025-01-22
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 12 | M2 |  | 2024-11-20
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 12 | M3 |  | 2024-12-21
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 13 | M1 |  | 2025-02-10
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 13 | M2 |  | 2025-01-22
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 13 | M3 |  | 2025-02-24
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 12 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 12 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 12 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 12 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 8 | M1 |  | 2024-11-20
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 8 | M2 |  | 2024-12-20
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 8 | M3 |  | 2024-11-25
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 8 | M4 |  | 2025-02-28
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 9 | M1 |  | 2025-01-11
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 9 | M2 |  | 2024-12-03
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 9 | M3 |  | 2024-12-02
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 10 | M1 |  | 2025-01-15
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 10 | M2 |  | 2024-12-09
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 10 | M3 |  | 2024-12-28
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 10 | M4 |  | 2025-02-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 11 | M1 |  | 2025-02-08
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 11 | M2 |  | 2025-02-28
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 11 | M3 |  | 2024-12-13
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 11 | M4 |  | 2025-03-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 11 | M5 |  | 2025-02-15
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 12 | M1 |  | 2025-01-18
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 12 | M2 |  | 2024-11-18
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 12 | M3 |  | 2024-12-11
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 13 | M1 |  | 2025-02-06
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 13 | M2 |  | 2025-01-17
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 13 | M3 |  | 2025-01-04
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 11 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 11 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 11 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 11 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 8 | M1 |  | 2024-11-18
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 8 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 8 | M2 |  | 2024-12-18
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 8 | M3 |  | 2024-11-14
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 8 | M4 |  | 2024-11-25
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 8 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 9 | M1 |  | 2025-01-09
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 9 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 9 | M2 |  | 2024-11-30
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 9 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 9 | M3 |  | 2024-11-29
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 10 | M1 |  | 2025-01-11
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 10 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 10 | M2 |  | 2024-12-06
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 10 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 10 | M3 |  | 2024-12-26
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 10 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 10 | M4 |  | 2025-01-24
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 10 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 11 | M1 |  | 2024-12-10
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 11 | M2 |  | 2024-12-10
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 11 | M3 |  | 2024-12-11
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 11 | M4 |  | 2024-12-30
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 11 | M5 |  | 2024-12-23
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 12 | M1 |  | 2025-01-17
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 12 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 12 | M2 |  | 2024-11-14
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 12 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 12 | M3 |  | 2024-12-13
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 12 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 13 | M1 |  | 2025-02-04
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 13 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 13 | M2 |  | 2025-01-15
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 13 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 13 | M3 |  | 2025-01-02
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 13 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 10 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 10 | 13 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 10 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 10 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 8 | M1 |  | 2024-11-14
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 8 | M1 |  | 2025-03-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 8 | M2 |  | 2024-12-12
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 8 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 8 | M3 |  | 2024-11-11
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 8 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 8 | M4 |  | 2024-11-21
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 8 | M4 |  | 2025-03-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 9 | M1 |  | 2025-01-07
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 9 | M1 |  | 2025-03-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 9 | M2 |  | 2024-11-28
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 9 | M2 |  | 2025-03-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 9 | M3 |  | 2024-11-27
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 9 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 10 | M1 |  | 2025-01-09
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 10 | M1 |  | 2025-03-07
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 10 | M2 |  | 2024-12-03
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 10 | M2 |  | 2025-03-07
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 10 | M3 |  | 2024-12-12
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 10 | M3 |  | 2025-03-07
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 10 | M4 |  | 2025-01-17
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 10 | M4 |  | 2025-03-07
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 11 | M1 |  | 2024-12-07
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 11 | M1 |  | 2025-03-05
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 11 | M2 |  | 2024-12-07
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 11 | M2 |  | 2025-03-05
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 11 | M3 |  | 2024-12-09
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 11 | M3 |  | 2025-03-05
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 11 | M4 |  | 2024-12-26
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 11 | M5 |  | 2024-12-20
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 11 | M5 |  | 2025-03-05
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 12 | M1 |  | 2025-01-16
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 12 | M1 |  | 2025-03-05
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 12 | M2 |  | 2024-11-12
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 12 | M2 |  | 2025-03-05
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 12 | M3 |  | 2024-12-11
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 12 | M3 |  | 2025-03-05
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 13 | M1 |  | 2025-01-16
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 13 | M1 |  | 2025-03-06
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 13 | M2 |  | 2025-01-13
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 13 | M2 |  | 2025-03-06
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 13 | M3 |  | 2024-12-30
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 13 | M3 |  | 2025-03-06
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 9 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 9 | 13 | M4 |  | 2025-03-06
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 9 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 9 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 8 | M1 |  | 2024-11-12
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 8 | M1 |  | 2025-02-26
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 8 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 8 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 8 | M2 |  | 2024-12-10
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 8 | M2 |  | 2025-02-27
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 8 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 8 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 8 | M3 |  | 2024-11-07
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 8 | M3 |  | 2025-02-26
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 8 | M4 |  | 2024-11-15
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 8 | M4 |  | 2025-02-25
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 9 | M1 |  | 2024-11-28
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 9 | M1 |  | 2025-02-26
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 9 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 9 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 9 | M2 |  | 2024-11-26
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 9 | M2 |  | 2025-02-25
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 9 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 9 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 9 | M3 |  | 2024-11-25
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 9 | M3 |  | 2025-02-25
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 9 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 9 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 10 | M1 |  | 2025-01-07
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 10 | M1 |  | 2025-02-28
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 10 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 10 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 10 | M2 |  | 2024-11-30
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 10 | M2 |  | 2025-02-25
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 10 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 10 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 10 | M3 |  | 2024-12-10
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 10 | M3 |  | 2025-02-27
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 10 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 10 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 10 | M4 |  | 2025-01-14
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 10 | M4 |  | 2025-02-27
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 10 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 10 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 11 | M1 |  | 2024-12-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 11 | M1 |  | 2025-02-24
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 11 | M2 |  | 2024-12-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 11 | M2 |  | 2025-02-25
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 11 | M3 |  | 2024-12-06
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 11 | M3 |  | 2025-02-26
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 11 | M4 |  | 2024-12-19
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 11 | M4 |  | 2025-02-24
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 11 | M5 |  | 2024-12-18
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 11 | M5 |  | 2025-02-24
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 12 | M1 |  | 2025-01-14
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 12 | M1 |  | 2025-02-24
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 12 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 12 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 12 | M2 |  | 2024-11-09
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 12 | M2 |  | 2025-02-24
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 12 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 12 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 12 | M3 |  | 2024-12-09
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 12 | M3 |  | 2025-02-24
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 12 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 12 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 13 | M1 |  | 2024-12-11
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 13 | M1 |  | 2025-02-25
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 13 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 13 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 13 | M2 |  | 2025-01-10
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 13 | M2 |  | 2025-02-28
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 13 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 13 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 13 | M3 |  | 2024-12-27
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 13 | M3 |  | 2025-02-27
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 13 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 13 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 8 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 8 | 13 | M4 |  | 2025-02-27
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 8 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 8 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 8 | M1 |  | 2024-11-08
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 8 | M1 |  | 2025-02-19
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 8 | M1 |  | 2025-03-05
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 8 | M1 |  | 2025-03-05
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 8 | M2 |  | 2024-11-12
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 8 | M2 |  | 2025-02-19
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 8 | M2 |  | 2025-03-05
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 8 | M2 |  | 2025-03-05
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 8 | M3 |  | 2024-11-04
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 8 | M3 |  | 2025-02-19
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 8 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 8 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 8 | M4 |  | 2024-11-11
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 8 | M4 |  | 2025-02-19
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 8 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 8 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 9 | M1 |  | 2024-11-26
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 9 | M1 |  | 2025-02-13
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 9 | M1 |  | 2025-03-03
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 9 | M1 |  | 2025-03-03
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 9 | M2 |  | 2024-11-23
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 9 | M2 |  | 2025-02-12
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 9 | M2 |  | 2025-03-03
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 9 | M2 |  | 2025-03-03
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 9 | M3 |  | 2024-11-22
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 9 | M3 |  | 2025-02-13
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 9 | M3 |  | 2025-03-03
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 9 | M3 |  | 2025-03-03
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 10 | M1 |  | 2024-11-28
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 10 | M1 |  | 2025-02-17
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 10 | M1 |  | 2025-03-01
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 10 | M1 |  | 2025-03-01
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 10 | M2 |  | 2024-11-25
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 10 | M2 |  | 2025-02-17
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 10 | M2 |  | 2025-03-01
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 10 | M2 |  | 2025-03-01
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 10 | M3 |  | 2024-12-06
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 10 | M3 |  | 2025-02-17
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 10 | M3 |  | 2025-03-01
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 10 | M3 |  | 2025-03-01
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 10 | M4 |  | 2024-12-03
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 10 | M4 |  | 2025-02-17
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 10 | M4 |  | 2025-03-03
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 10 | M4 |  | 2025-03-03
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 11 | M1 |  | 2024-12-03
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 11 | M1 |  | 2025-02-10
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 11 | M2 |  | 2024-12-02
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 11 | M2 |  | 2025-02-11
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 11 | M3 |  | 2024-12-04
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 11 | M3 |  | 2025-02-12
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 11 | M4 |  | 2024-12-21
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 11 | M4 |  | 2025-02-12
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 11 | M5 |  | 2024-12-16
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 11 | M5 |  | 2025-02-11
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 11 | M5 |  | 2025-03-08
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 11 | M5 |  | 2025-03-08
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 12 | M1 |  | 2024-11-22
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 12 | M1 |  | 2025-02-14
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 12 | M1 |  | 2025-02-21
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 12 | M1 |  | 2025-02-21
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 12 | M2 |  | 2024-11-07
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 12 | M2 |  | 2025-02-14
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 12 | M2 |  | 2025-02-21
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 12 | M2 |  | 2025-02-21
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 12 | M3 |  | 2024-11-04
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 12 | M3 |  | 2025-02-13
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 12 | M3 |  | 2025-02-22
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 12 | M3 |  | 2025-02-22
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 13 | M1 |  | 2025-01-22
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 13 | M1 |  | 2025-02-14
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 13 | M1 |  | 2025-02-22
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 13 | M1 |  | 2025-02-22
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 13 | M2 |  | 2024-12-04
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 13 | M2 |  | 2025-02-14
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 13 | M2 |  | 2025-02-22
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 13 | M2 |  | 2025-02-22
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 13 | M3 |  | 2024-12-24
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 13 | M3 |  | 2025-02-14
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 13 | M3 |  | 2025-02-26
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 13 | M3 |  | 2025-02-26
Fabrication | PPVC | Casting |  |  |  | 7 |  | 7 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 7 | 13 | M4 |  | 2025-02-14
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 7 | 13 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 7 | 13 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 8 | M1 |  | 2024-11-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 8 | M1 |  | 2025-02-07
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 8 | M1 |  | 2025-02-18
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 8 | M1 |  | 2025-02-18
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 8 | M2 |  | 2024-11-08
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 8 | M2 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 8 | M2 |  | 2025-02-18
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 8 | M2 |  | 2025-02-18
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 8 | M3 |  | 2024-10-30
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 8 | M3 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 8 | M3 |  | 2025-02-19
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 8 | M3 |  | 2025-02-19
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 8 | M4 |  | 2024-11-08
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 8 | M4 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 8 | M4 |  | 2025-02-19
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 8 | M4 |  | 2025-02-19
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 9 | M1 |  | 2024-11-23
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 9 | M1 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 9 | M1 |  | 2025-02-17
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 9 | M1 |  | 2025-02-17
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 9 | M2 |  | 2024-11-21
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 9 | M2 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 9 | M2 |  | 2025-02-17
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 9 | M2 |  | 2025-02-17
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 9 | M3 |  | 2024-11-19
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 9 | M3 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 9 | M3 |  | 2025-02-17
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 9 | M3 |  | 2025-02-17
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 10 | M1 |  | 2024-11-26
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 10 | M1 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 10 | M1 |  | 2025-02-13
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 10 | M1 |  | 2025-02-13
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 10 | M2 |  | 2024-11-22
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 10 | M2 |  | 2025-02-07
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 10 | M2 |  | 2025-02-14
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 10 | M2 |  | 2025-02-14
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 10 | M3 |  | 2024-12-23
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 10 | M3 |  | 2025-02-10
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 10 | M3 |  | 2025-02-14
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 10 | M3 |  | 2025-02-14
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 10 | M4 |  | 2024-11-29
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 10 | M4 |  | 2025-02-07
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 10 | M4 |  | 2025-02-15
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 10 | M4 |  | 2025-02-15
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 11 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 11 | M5
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 12 | M1 |  | 2024-11-18
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 12 | M1 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 12 | M1 |  | 2025-02-11
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 12 | M1 |  | 2025-02-11
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 12 | M2 |  | 2024-11-05
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 12 | M2 |  | 2025-02-07
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 12 | M2 |  | 2025-02-11
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 12 | M2 |  | 2025-02-11
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 12 | M3 |  | 2024-11-01
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 12 | M3 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 12 | M3 |  | 2025-02-11
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 12 | M3 |  | 2025-02-11
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 13 | M1 |  | 2024-12-14
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 13 | M1 |  | 2025-02-07
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 13 | M1 |  | 2025-02-12
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 13 | M1 |  | 2025-02-12
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 13 | M2 |  | 2024-12-02
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 13 | M2 |  | 2025-02-07
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 13 | M2 |  | 2025-02-12
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 13 | M2 |  | 2025-02-12
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 13 | M3 |  | 2024-12-21
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 13 | M3 |  | 2025-02-07
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 13 | M3 |  | 2025-02-14
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 13 | M3 |  | 2025-02-14
Fabrication | PPVC | Casting |  |  |  | 7 |  | 6 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 6 | 13 | M4 |  | 2025-02-07
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 6 | 13 | M4 |  | 2025-02-20
Fabrication | PPVC | Installation |  |  |  | 7 |  | 6 | 13 | M4 |  | 2025-02-20
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 8 | M1 |  | 2024-10-30
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 8 | M1 |  | 2025-01-22
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 8 | M1 |  | 2025-02-08
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 8 | M1 |  | 2025-02-08
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 8 | M2 |  | 2024-11-06
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 8 | M2 |  | 2025-01-22
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 8 | M2 |  | 2025-02-10
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 8 | M2 |  | 2025-02-10
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 8 | M3 |  | 2024-10-28
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 8 | M3 |  | 2025-01-22
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 8 | M3 |  | 2025-02-10
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 8 | M3 |  | 2025-02-10
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 8 | M4 |  | 2024-11-06
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 8 | M4 |  | 2025-01-22
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 8 | M4 |  | 2025-02-10
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 8 | M4 |  | 2025-02-10
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 9 | M1 |  | 2024-11-18
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 9 | M1 |  | 2025-01-11
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 9 | M1 |  | 2025-02-08
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 9 | M1 |  | 2025-02-08
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 9 | M2 |  | 2024-11-19
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 9 | M2 |  | 2025-01-11
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 9 | M2 |  | 2025-02-08
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 9 | M2 |  | 2025-02-08
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 9 | M3 |  | 2024-11-16
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 9 | M3 |  | 2025-01-11
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 9 | M3 |  | 2025-02-08
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 9 | M3 |  | 2025-02-08
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 10 | M1 |  | 2024-11-23
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 10 | M1 |  | 2025-01-13
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 10 | M1 |  | 2025-02-07
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 10 | M1 |  | 2025-02-07
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 10 | M2 |  | 2024-11-19
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 10 | M2 |  | 2025-01-13
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 10 | M2 |  | 2025-02-07
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 10 | M2 |  | 2025-02-07
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 10 | M3 |  | 2024-12-20
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 10 | M3 |  | 2025-01-13
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 10 | M3 |  | 2025-02-07
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 10 | M3 |  | 2025-02-07
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 10 | M4 |  | 2024-11-27
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 10 | M4 |  | 2025-01-22
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 10 | M4 |  | 2025-02-08
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 10 | M4 |  | 2025-02-08
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 11 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 11 | M5
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 12 | M1 |  | 2024-11-15
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 12 | M1 |  | 2025-01-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 12 | M1 |  | 2025-02-05
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 12 | M1 |  | 2025-02-05
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 12 | M2 |  | 2024-11-02
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 12 | M2 |  | 2025-01-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 12 | M2 |  | 2025-02-06
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 12 | M2 |  | 2025-02-06
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 12 | M3 |  | 2024-10-29
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 12 | M3 |  | 2025-01-08
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 12 | M3 |  | 2025-02-06
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 12 | M3 |  | 2025-02-06
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 13 | M1 |  | 2024-12-09
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 13 | M1 |  | 2025-01-21
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 13 | M1 |  | 2025-02-06
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 13 | M1 |  | 2025-02-06
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 13 | M2 |  | 2024-11-29
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 13 | M2 |  | 2025-01-21
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 13 | M2 |  | 2025-02-06
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 13 | M2 |  | 2025-02-06
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 13 | M3 |  | 2024-12-19
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 13 | M3 |  | 2025-01-21
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 13 | M3 |  | 2025-02-06
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 13 | M3 |  | 2025-02-06
Fabrication | PPVC | Casting |  |  |  | 7 |  | 5 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 5 | 13 | M4 |  | 2025-01-21
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 5 | 13 | M4 |  | 2025-02-07
Fabrication | PPVC | Installation |  |  |  | 7 |  | 5 | 13 | M4 |  | 2025-02-07
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 8 | M1 |  | 2024-10-26
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 8 | M1 |  | 2025-01-04
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 8 | M1 |  | 2025-02-04
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 8 | M1 |  | 2025-02-04
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 8 | M2 |  | 2024-11-04
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 8 | M2 |  | 2025-01-04
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 8 | M2 |  | 2025-02-04
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 8 | M2 |  | 2025-02-04
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 8 | M3 |  | 2024-10-24
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 8 | M3 |  | 2025-01-04
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 8 | M3 |  | 2025-02-05
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 8 | M3 |  | 2025-02-05
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 8 | M4 |  | 2024-11-04
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 8 | M4 |  | 2025-01-04
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 8 | M4 |  | 2025-02-04
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 8 | M4 |  | 2025-02-04
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 9 | M1 |  | 2024-11-13
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 9 | M1 |  | 2024-12-30
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 9 | M1 |  | 2025-02-03
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 9 | M1 |  | 2025-02-03
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 9 | M2 |  | 2024-11-16
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 9 | M2 |  | 2024-12-30
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 9 | M2 |  | 2025-02-03
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 9 | M2 |  | 2025-02-03
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 9 | M3 |  | 2024-11-15
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 9 | M3 |  | 2024-12-30
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 9 | M3 |  | 2025-02-04
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 9 | M3 |  | 2025-02-04
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 10 | M1 |  | 2024-11-21
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 10 | M1 |  | 2024-12-18
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 10 | M1 |  | 2025-02-03
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 10 | M1 |  | 2025-02-03
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 10 | M2 |  | 2024-11-16
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 10 | M2 |  | 2024-12-18
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 10 | M2 |  | 2025-02-03
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 10 | M2 |  | 2025-02-03
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 10 | M3 |  | 2024-12-16
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 10 | M3 |  | 2024-12-20
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 10 | M3 |  | 2025-02-03
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 10 | M3 |  | 2025-02-03
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 10 | M4 |  | 2024-11-25
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 10 | M4 |  | 2024-12-18
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 10 | M4 |  | 2025-02-03
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 10 | M4 |  | 2025-02-03
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 11 | M1
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 11 | M1
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 11 | M1
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 11 | M1
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 11 | M2
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 11 | M2
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 11 | M2
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 11 | M2
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 11 | M3
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 11 | M3
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 11 | M3
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 11 | M3
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 11 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 11 | M4
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 11 | M4
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 11 | M4
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 11 | M5
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 11 | M5
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 11 | M5
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 11 | M5
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 12 | M1 |  | 2024-11-12
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 12 | M1 |  | 2024-12-27
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 12 | M1 |  | 2025-01-24
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 12 | M1 |  | 2025-01-24
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 12 | M2 |  | 2024-10-30
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 12 | M2 |  | 2024-12-27
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 12 | M2 |  | 2025-01-24
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 12 | M2 |  | 2025-01-24
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 12 | M3 |  | 2024-10-25
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 12 | M3 |  | 2024-12-27
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 12 | M3 |  | 2025-01-24
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 12 | M3 |  | 2025-01-24
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 13 | M1 |  | 2024-12-06
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 13 | M1 |  | 2024-12-19
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 13 | M1 |  | 2025-01-24
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 13 | M1 |  | 2025-01-24
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 13 | M2 |  | 2024-11-27
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 13 | M2 |  | 2024-12-19
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 13 | M2 |  | 2025-01-27
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 13 | M2 |  | 2025-01-27
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 13 | M3 |  | 2024-12-16
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 13 | M3 |  | 2024-12-20
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 13 | M3 |  | 2025-01-27
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 13 | M3 |  | 2025-01-27
Fabrication | PPVC | Casting |  |  |  | 7 |  | 4 | 13 | M4
Fabrication | PPVC | Delivery |  |  |  | 7 |  | 4 | 13 | M4 |  | 2024-12-19
Fabrication | PPVC | Fit Out |  |  |  | 7 |  | 4 | 13 | M4 |  | 2025-01-27
Fabrication | PPVC | Installation |  |  |  | 7 |  | 4 | 13 | M4 |  | 2025-01-27
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 1 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 1 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 1 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 1 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 2 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 2 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 2 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 3 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 3 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 3 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 3 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 3 | M5
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 4 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 4 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 4 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 4 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 5 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 5 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 5 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 6 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 6 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 6 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 7 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 7 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 7 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 27 | 7 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 27 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 27 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 27 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 1 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 1 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 1 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 1 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 2 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 2 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 2 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 3 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 3 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 3 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 3 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 3 | M5
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 4 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 4 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 4 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 4 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 5 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 5 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 5 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 6 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 6 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 6 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 7 | M1 |  | 2024-10-16
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 7 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 7 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 26 | 7 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 26 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 26 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 26 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 1 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 1 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 1 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 1 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 2 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 2 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 2 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 3 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 3 | M2 |  | 2025-03-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 3 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 3 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 3 | M5
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 4 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 4 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 4 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 4 | M4 |  | 2025-03-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 5 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 5 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 5 | M3 |  | 2025-01-16
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 6 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 6 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 6 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 7 | M1 |  | 2024-10-12
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 7 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 7 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 25 | 7 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 25 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 25 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 25 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 1 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 1 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 1 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 1 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 2 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 2 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 2 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 3 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 3 | M2 |  | 2025-03-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 3 | M3 |  | 2025-02-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 3 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 3 | M5
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 4 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 4 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 4 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 4 | M4 |  | 2025-03-01
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 5 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 5 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 5 | M3 |  | 2025-01-11
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 6 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 6 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 6 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 7 | M1 |  | 2024-10-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 7 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 7 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 24 | 7 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 24 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 24 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 24 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 1 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 1 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 1 | M3 |  | 2025-02-17
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 1 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 2 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 2 | M2 |  | 2025-03-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 2 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 3 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 3 | M2 |  | 2025-03-01
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 3 | M3 |  | 2025-02-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 3 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 3 | M5
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 4 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 4 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 4 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 4 | M4 |  | 2025-02-27
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 5 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 5 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 5 | M3 |  | 2025-01-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 6 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 6 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 6 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 7 | M1 |  | 2024-10-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 7 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 7 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 23 | 7 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 23 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 23 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 23 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 1 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 1 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 1 | M3 |  | 2025-02-15
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 1 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 2 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 2 | M2 |  | 2025-03-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 2 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 3 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 3 | M2 |  | 2025-02-27
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 3 | M3 |  | 2025-02-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 3 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 3 | M5
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 4 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 4 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 4 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 4 | M4 |  | 2025-02-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 5 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 5 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 5 | M3 |  | 2025-01-09
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 6 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 6 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 6 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 7 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 7 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 7 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 22 | 7 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 22 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 22 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 22 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 1 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 1 | M2 |  | 2025-01-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 1 | M3 |  | 2025-02-13
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 1 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 2 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 2 | M2 |  | 2025-02-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 2 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 3 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 3 | M2 |  | 2025-02-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 3 | M3 |  | 2025-02-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 3 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 3 | M5
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 4 | M1 |  | 2025-02-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 4 | M2 |  | 2025-02-26
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 4 | M3 |  | 2025-02-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 4 | M4 |  | 2025-02-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 5 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 5 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 5 | M3 |  | 2025-01-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 6 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 6 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 6 | M3 |  | 2025-02-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 7 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 7 | M2 |  | 2025-02-12
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 7 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 21 | 7 | M4 |  | 2025-03-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 21 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 21 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 21 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 1 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 1 | M2 |  | 2025-01-16
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 1 | M3 |  | 2025-02-11
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 1 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 2 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 2 | M2 |  | 2025-02-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 2 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 3 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 3 | M2 |  | 2025-02-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 3 | M3 |  | 2025-02-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 3 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 3 | M5
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 4 | M1 |  | 2025-01-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 4 | M2 |  | 2025-02-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 4 | M3 |  | 2025-02-21
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 4 | M4 |  | 2025-02-21
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 5 | M1 |  | 2025-02-17
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 5 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 5 | M3 |  | 2024-10-02
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 6 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 6 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 6 | M3 |  | 2025-02-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 7 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 7 | M2 |  | 2025-02-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 7 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 20 | 7 | M4 |  | 2025-03-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 20 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 20 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 20 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 1 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 1 | M2 |  | 2025-01-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 1 | M3 |  | 2025-02-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 1 | M4 |  | 2025-03-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 2 | M1 |  | 2025-03-01
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 2 | M2 |  | 2025-01-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 2 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 3 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 3 | M2 |  | 2025-02-20
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 3 | M3 |  | 2025-01-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 3 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 3 | M5
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 4 | M1 |  | 2025-01-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 4 | M2 |  | 2025-02-21
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 4 | M3 |  | 2025-02-19
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 4 | M4 |  | 2025-02-19
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 5 | M1 |  | 2025-02-13
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 5 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 5 | M3 |  | 2024-09-25
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 6 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 6 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 6 | M3 |  | 2025-02-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 7 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 7 | M2 |  | 2025-02-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 7 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 19 | 7 | M4 |  | 2025-03-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 19 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 19 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 19 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 1 | M1 |  | 2025-03-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 1 | M2 |  | 2025-01-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 1 | M3 |  | 2025-02-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 1 | M4 |  | 2025-03-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 2 | M1 |  | 2025-02-26
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 2 | M2 |  | 2025-01-23
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 2 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 3 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 3 | M2 |  | 2025-02-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 3 | M3 |  | 2025-01-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 3 | M4 |  | 2025-02-12
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 3 | M5
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 4 | M1 |  | 2025-01-17
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 4 | M2 |  | 2025-02-19
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 4 | M3 |  | 2025-02-17
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 4 | M4 |  | 2025-02-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 5 | M1 |  | 2025-02-11
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 5 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 5 | M3 |  | 2024-09-23
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 6 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 6 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 6 | M3 |  | 2025-01-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 7 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 7 | M2 |  | 2025-02-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 7 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 18 | 7 | M4 |  | 2025-03-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 18 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 18 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 18 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 1 | M1 |  | 2024-12-30
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 1 | M2 |  | 2025-01-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 1 | M3 |  | 2025-01-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 1 | M4 |  | 2025-03-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 2 | M1 |  | 2025-02-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 2 | M2 |  | 2025-01-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 2 | M3 |  | 2025-01-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 3 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 3 | M2 |  | 2025-02-17
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 3 | M3 |  | 2025-01-15
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 3 | M4 |  | 2025-02-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 3 | M5 |  | 2025-02-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 4 | M1 |  | 2025-01-15
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 4 | M2 |  | 2025-02-17
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 4 | M3 |  | 2025-02-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 4 | M4 |  | 2025-02-12
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 5 | M1 |  | 2025-02-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 5 | M2 |  | 2025-02-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 5 | M3 |  | 2025-01-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 6 | M1 |  | 2025-02-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 6 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 6 | M3 |  | 2025-01-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 7 | M1 |  | 2025-02-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 7 | M2 |  | 2025-02-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 7 | M3 |  | 2025-02-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 17 | 7 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 17 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 17 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 17 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 1 | M1 |  | 2024-12-27
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 1 | M2 |  | 2025-01-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 1 | M3 |  | 2025-01-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 1 | M4 |  | 2025-03-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 2 | M1 |  | 2025-02-21
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 2 | M2 |  | 2025-01-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 2 | M3 |  | 2025-01-02
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 3 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 3 | M2 |  | 2025-02-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 3 | M3 |  | 2025-01-13
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 3 | M4 |  | 2025-02-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 3 | M5 |  | 2025-02-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 4 | M1 |  | 2025-01-13
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 4 | M2 |  | 2025-02-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 4 | M3 |  | 2025-01-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 4 | M4 |  | 2025-02-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 5 | M1 |  | 2025-02-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 5 | M2 |  | 2025-02-20
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 5 | M3 |  | 2025-01-01
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 6 | M1 |  | 2025-02-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 6 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 6 | M3 |  | 2025-01-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 7 | M1 |  | 2025-02-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 7 | M2 |  | 2025-01-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 7 | M3 |  | 2025-02-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 16 | 7 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 16 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 16 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 16 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 1 | M1 |  | 2024-12-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 1 | M2 |  | 2025-01-01
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 1 | M3 |  | 2025-01-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 1 | M4 |  | 2025-03-01
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 2 | M1 |  | 2025-02-19
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 2 | M2 |  | 2025-01-16
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 2 | M3 |  | 2025-01-02
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 3 | M1 |  | 2025-01-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 3 | M2 |  | 2025-02-12
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 3 | M3 |  | 2025-01-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 3 | M4 |  | 2025-02-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 3 | M5 |  | 2025-02-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 4 | M1 |  | 2025-01-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 4 | M2 |  | 2025-01-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 4 | M3 |  | 2025-01-09
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 4 | M4 |  | 2025-02-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 5 | M1 |  | 2025-02-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 5 | M2 |  | 2025-02-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 5 | M3 |  | 2024-09-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 6 | M1 |  | 2025-02-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 6 | M2 |  | 2025-02-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 6 | M3 |  | 2025-01-16
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 7 | M1 |  | 2025-02-20
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 7 | M2 |  | 2025-01-23
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 7 | M3 |  | 2025-02-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 15 | 7 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 15 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 15 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 15 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 1 | M1 |  | 2024-12-21
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 1 | M2 |  | 2024-12-26
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 1 | M3 |  | 2024-12-31
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 1 | M4 |  | 2025-01-15
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 2 | M1 |  | 2025-02-17
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 2 | M2 |  | 2025-01-15
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 2 | M3 |  | 2024-12-30
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 3 | M1 |  | 2025-01-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 3 | M2 |  | 2025-02-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 3 | M3 |  | 2025-01-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 3 | M4 |  | 2025-01-25
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 3 | M5 |  | 2025-01-25
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 4 | M1 |  | 2025-01-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 4 | M2 |  | 2025-01-11
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 4 | M3 |  | 2025-01-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 4 | M4 |  | 2025-02-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 5 | M1 |  | 2025-01-13
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 5 | M2 |  | 2025-02-15
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 5 | M3 |  | 2024-09-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 6 | M1 |  | 2025-01-25
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 6 | M2 |  | 2025-01-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 6 | M3 |  | 2025-01-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 7 | M1 |  | 2025-02-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 7 | M2 |  | 2025-01-21
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 7 | M3 |  | 2025-01-25
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 14 | 7 | M4 |  | 2025-03-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 14 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 14 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 14 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 1 | M1 |  | 2024-12-19
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 1 | M2 |  | 2024-12-20
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 1 | M3 |  | 2024-12-28
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 1 | M4 |  | 2025-01-13
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 2 | M1 |  | 2025-02-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 2 | M2 |  | 2025-01-13
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 2 | M3 |  | 2024-12-27
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 3 | M1 |  | 2025-01-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 3 | M2 |  | 2025-01-25
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 3 | M3 |  | 2025-01-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 3 | M4 |  | 2025-01-23
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 3 | M5 |  | 2025-01-23
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 4 | M1 |  | 2025-01-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 4 | M2 |  | 2025-01-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 4 | M3 |  | 2025-01-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 4 | M4 |  | 2025-02-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 5 | M1 |  | 2024-10-01
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 5 | M2 |  | 2025-02-12
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 5 | M3 |  | 2024-09-28
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 6 | M1 |  | 2025-01-23
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 6 | M2 |  | 2025-01-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 6 | M3 |  | 2025-01-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 7 | M1 |  | 2025-02-01
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 7 | M2 |  | 2025-01-17
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 7 | M3 |  | 2025-01-23
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 13 | 7 | M4 |  | 2025-03-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 13 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 13 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 13 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 1 | M1 |  | 2024-11-20
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 1 | M2 |  | 2024-10-11
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 1 | M3 |  | 2024-10-17
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 1 | M4 |  | 2025-01-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 2 | M1 |  | 2024-10-19
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 2 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 2 | M2 |  | 2024-10-25
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 2 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 2 | M3 |  | 2024-10-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 3 | M1 |  | 2025-01-02
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 3 | M2 |  | 2025-01-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 3 | M3 |  | 2024-11-28
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 3 | M4 |  | 2024-10-21
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 3 | M5 |  | 2024-09-28
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 4 | M1 |  | 2024-10-23
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 4 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 4 | M2 |  | 2025-01-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 4 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 4 | M3 |  | 2024-12-30
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 4 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 4 | M4 |  | 2025-02-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 4 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 5 | M1 |  | 2024-09-27
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 5 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 5 | M2 |  | 2025-02-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 5 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 5 | M3 |  | 2024-09-20
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 5 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 6 | M1 |  | 2024-10-02
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 6 | M2 |  | 2024-10-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 6 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 6 | M3 |  | 2024-10-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 7 | M1 |  | 2024-11-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 7 | M2 |  | 2024-11-02
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 7 | M3 |  | 2024-11-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 12 | 7 | M4 |  | 2025-02-20
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 12 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 12 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 12 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 1 | M1 |  | 2024-11-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 1 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 1 | M2 |  | 2024-10-09
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 1 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 1 | M3 |  | 2024-10-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 1 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 1 | M4 |  | 2025-01-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 2 | M1 |  | 2024-10-16
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 2 | M1 |  | 2025-03-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 2 | M2 |  | 2024-10-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 2 | M2 |  | 2025-03-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 2 | M3 |  | 2024-10-11
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 2 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 3 | M1 |  | 2025-12-30
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 3 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 3 | M2 |  | 2025-01-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 3 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 3 | M3 |  | 2024-11-26
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 3 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 3 | M4 |  | 2024-10-17
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 3 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 3 | M5 |  | 2024-09-26
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 3 | M5
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 4 | M1 |  | 2024-10-21
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 4 | M1 |  | 2025-03-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 4 | M2 |  | 2025-01-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 4 | M2 |  | 2025-03-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 4 | M3 |  | 2024-11-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 4 | M3 |  | 2025-03-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 4 | M4 |  | 2025-01-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 4 | M4 |  | 2025-03-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 5 | M1 |  | 2024-09-23
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 5 | M1 |  | 2025-03-07
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 5 | M2 |  | 2024-12-11
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 5 | M2 |  | 2025-03-07
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 5 | M3 |  | 2024-12-11
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 5 | M3 |  | 2025-03-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 6 | M1 |  | 2024-09-30
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 6 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 6 | M2 |  | 2025-01-17
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 6 | M2 |  | 2025-03-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 6 | M3 |  | 2024-10-02
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 6 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 7 | M1 |  | 2024-11-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 7 | M2 |  | 2024-10-30
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 7 | M3 |  | 2024-11-01
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 7 | M3 |  | 2025-03-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 11 | 7 | M4 |  | 2025-02-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 11 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 11 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 11 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 1 | M1 |  | 2024-11-15
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 1 | M1 |  | 2025-03-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 1 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 1 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 1 | M2 |  | 2024-10-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 1 | M2 |  | 2025-03-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 1 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 1 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 1 | M3 |  | 2024-10-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 1 | M3 |  | 2025-03-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 1 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 1 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 1 | M4 |  | 2025-01-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 1 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 1 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 1 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 2 | M1 |  | 2024-10-12
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 2 | M1 |  | 2025-03-04
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 2 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 2 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 2 | M2 |  | 2024-09-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 2 | M2 |  | 2025-03-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 2 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 2 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 2 | M3 |  | 2024-10-09
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 2 | M3 |  | 2025-03-01
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 2 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 2 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 3 | M1 |  | 2024-12-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 3 | M1 |  | 2025-03-04
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 3 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 3 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 3 | M2 |  | 2024-09-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 3 | M2 |  | 2025-03-05
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 3 | M3 |  | 2024-11-21
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 3 | M3 |  | 2025-03-04
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 3 | M4 |  | 2024-09-09
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 3 | M4 |  | 2025-03-04
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 3 | M5 |  | 2024-09-23
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 3 | M5 |  | 2025-03-04
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 4 | M1 |  | 2024-10-19
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 4 | M1 |  | 2025-02-28
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 4 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 4 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 4 | M2 |  | 2025-01-02
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 4 | M2 |  | 2025-02-28
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 4 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 4 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 4 | M3 |  | 2024-11-12
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 4 | M3 |  | 2025-02-28
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 4 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 4 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 4 | M4 |  | 2025-01-02
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 4 | M4 |  | 2025-02-28
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 4 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 4 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 5 | M1 |  | 2024-09-20
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 5 | M1 |  | 2025-02-28
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 5 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 5 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 5 | M2 |  | 2024-12-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 5 | M2 |  | 2025-02-28
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 5 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 5 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 5 | M3 |  | 2024-12-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 5 | M3 |  | 2025-03-01
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 5 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 5 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 6 | M1 |  | 2024-09-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 6 | M1 |  | 2025-03-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 6 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 6 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 6 | M2 |  | 2024-10-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 6 | M2 |  | 2025-03-01
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 6 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 6 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 6 | M3 |  | 2024-09-30
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 6 | M3 |  | 2025-03-01
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 6 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 6 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 7 | M1 |  | 2024-11-02
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 7 | M1 |  | 2025-03-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 7 | M2 |  | 2024-10-26
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 7 | M2 |  | 2025-03-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 7 | M3 |  | 2024-10-29
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 7 | M3 |  | 2025-03-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 10 | 7 | M4 |  | 2024-10-30
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 10 | 7 | M4 |  | 2025-03-01
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 10 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 10 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 1 | M1 |  | 2024-11-13
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 1 | M1 |  | 2025-02-21
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 1 | M1 |  | 2025-03-07
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 1 | M1 |  | 2025-03-07
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 1 | M2 |  | 2024-10-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 1 | M2 |  | 2025-02-21
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 1 | M2 |  | 2025-03-07
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 1 | M2 |  | 2025-03-07
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 1 | M3 |  | 2024-10-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 1 | M3 |  | 2025-02-21
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 1 | M3 |  | 2025-03-08
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 1 | M3 |  | 2025-03-08
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 1 | M4 |  | 2024-10-21
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 1 | M4 |  | 2025-03-07
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 1 | M4 |  | 2025-03-07
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 1 | M4 |  | 2025-03-07
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 2 | M1 |  | 2024-08-23
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 2 | M1 |  | 2025-02-21
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 2 | M1 |  | 2025-03-08
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 2 | M1 |  | 2025-03-08
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 2 | M2 |  | 2024-09-12
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 2 | M2 |  | 2025-02-22
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 2 | M2 |  | 2025-03-08
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 2 | M2 |  | 2025-03-08
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 2 | M3 |  | 2024-09-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 2 | M3 |  | 2025-02-21
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 2 | M3 |  | 2025-03-08
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 2 | M3 |  | 2025-03-08
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 3 | M1 |  | 2024-12-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 3 | M1 |  | 2025-02-22
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 3 | M1 |  | 2025-03-08
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 3 | M1 |  | 2025-03-08
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 3 | M2 |  | 2024-09-16
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 3 | M2 |  | 2025-02-22
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 3 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 3 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 3 | M3 |  | 2024-11-13
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 3 | M3 |  | 2025-02-22
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 3 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 3 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 3 | M4 |  | 2024-09-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 3 | M4 |  | 2025-02-22
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 3 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 3 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 3 | M5 |  | 2024-09-20
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 3 | M5 |  | 2025-02-22
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 3 | M5
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 3 | M5
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 4 | M1 |  | 2024-10-17
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 4 | M1 |  | 2025-02-12
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 4 | M1 |  | 2025-03-01
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 4 | M1 |  | 2025-03-01
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 4 | M2 |  | 2024-12-31
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 4 | M2 |  | 2025-02-12
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 4 | M2 |  | 2025-03-03
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 4 | M2 |  | 2025-03-03
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 4 | M3 |  | 2024-10-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 4 | M3 |  | 2025-02-12
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 4 | M3 |  | 2025-03-03
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 4 | M3 |  | 2025-03-03
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 4 | M4 |  | 2024-12-31
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 4 | M4 |  | 2025-02-12
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 4 | M4 |  | 2025-03-03
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 4 | M4 |  | 2025-03-03
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 5 | M1 |  | 2024-09-17
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 5 | M1 |  | 2025-02-13
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 5 | M1 |  | 2025-03-03
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 5 | M1 |  | 2025-03-03
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 5 | M2 |  | 2024-12-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 5 | M2 |  | 2025-02-12
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 5 | M2 |  | 2025-03-03
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 5 | M2 |  | 2025-03-03
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 5 | M3 |  | 2024-09-17
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 5 | M3 |  | 2025-02-13
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 5 | M3 |  | 2025-03-04
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 5 | M3 |  | 2025-03-04
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 6 | M1 |  | 2024-09-20
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 6 | M1 |  | 2025-02-13
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 6 | M1 |  | 2025-03-05
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 6 | M1 |  | 2025-03-05
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 6 | M2 |  | 2024-10-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 6 | M2 |  | 2025-02-12
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 6 | M2 |  | 2025-03-05
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 6 | M2 |  | 2025-03-05
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 6 | M3 |  | 2024-09-27
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 6 | M3 |  | 2025-02-20
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 6 | M3 |  | 2025-03-05
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 6 | M3 |  | 2025-03-05
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 7 | M1 |  | 2024-10-28
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 7 | M1 |  | 2025-02-20
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 7 | M2 |  | 2024-10-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 7 | M2 |  | 2025-02-20
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 7 | M2 |  | 2025-03-07
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 7 | M2 |  | 2025-03-07
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 7 | M3 |  | 2024-10-25
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 7 | M3 |  | 2025-02-20
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 7 | M3 |  | 2025-03-06
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 7 | M3 |  | 2025-03-06
Fabrication | PPVC | Casting |  |  |  | 5 |  | 9 | 7 | M4 |  | 2024-10-28
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 9 | 7 | M4 |  | 2025-02-20
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 9 | 7 | M4 |  | 2025-03-06
Fabrication | PPVC | Installation |  |  |  | 5 |  | 9 | 7 | M4 |  | 2025-03-06
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 1 | M1 |  | 2024-11-11
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 1 | M1 |  | 2025-02-10
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 1 | M1 |  | 2025-02-26
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 1 | M1 |  | 2025-02-26
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 1 | M2 |  | 2024-09-28
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 1 | M2 |  | 2025-02-11
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 1 | M2 |  | 2025-02-26
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 1 | M2 |  | 2025-02-26
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 1 | M3 |  | 2024-10-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 1 | M3 |  | 2025-02-10
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 1 | M3 |  | 2025-02-26
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 1 | M3 |  | 2025-02-26
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 1 | M4 |  | 2024-10-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 1 | M4 |  | 2025-02-26
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 1 | M4 |  | 2025-02-26
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 1 | M4 |  | 2025-02-26
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 2 | M1 |  | 2024-08-20
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 2 | M1 |  | 2025-02-11
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 2 | M1 |  | 2025-02-27
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 2 | M1 |  | 2025-02-27
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 2 | M2 |  | 2024-09-09
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 2 | M2 |  | 2025-02-10
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 2 | M2 |  | 2025-02-27
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 2 | M2 |  | 2025-02-27
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 2 | M3 |  | 2024-08-30
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 2 | M3 |  | 2025-02-10
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 2 | M3 |  | 2025-02-27
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 2 | M3 |  | 2025-02-27
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 3 | M1 |  | 2024-08-29
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 3 | M1 |  | 2025-02-11
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 3 | M1 |  | 2025-02-28
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 3 | M1 |  | 2025-02-28
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 3 | M2 |  | 2024-09-13
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 3 | M2 |  | 2025-02-12
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 3 | M2 |  | 2025-02-28
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 3 | M2 |  | 2025-02-28
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 3 | M3 |  | 2024-11-09
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 3 | M3 |  | 2025-02-11
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 3 | M3 |  | 2025-02-28
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 3 | M3 |  | 2025-02-28
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 3 | M4 |  | 2024-09-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 3 | M4 |  | 2025-02-10
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 3 | M4 |  | 2025-03-01
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 3 | M4 |  | 2025-03-01
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 3 | M5 |  | 2024-09-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 3 | M5 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 3 | M5 |  | 2025-03-01
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 3 | M5 |  | 2025-03-01
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 4 | M1 |  | 2024-10-15
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 4 | M1 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 4 | M1 |  | 2025-02-19
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 4 | M1 |  | 2025-02-19
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 4 | M2 |  | 2024-12-27
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 4 | M2 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 4 | M2 |  | 2025-02-20
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 4 | M2 |  | 2025-02-20
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 4 | M3 |  | 2024-10-12
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 4 | M3 |  | 2025-02-11
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 4 | M3 |  | 2025-02-20
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 4 | M3 |  | 2025-02-20
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 4 | M4 |  | 2024-12-27
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 4 | M4 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 4 | M4 |  | 2025-02-20
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 4 | M4 |  | 2025-02-20
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 5 | M1 |  | 2024-09-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 5 | M1 |  | 2025-02-10
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 5 | M1 |  | 2025-02-21
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 5 | M1 |  | 2025-02-21
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 5 | M2 |  | 2024-09-19
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 5 | M2 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 5 | M2 |  | 2025-02-21
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 5 | M2 |  | 2025-02-21
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 5 | M3 |  | 2024-09-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 5 | M3 |  | 2025-02-10
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 5 | M3 |  | 2025-02-21
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 5 | M3 |  | 2025-02-21
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 6 | M1 |  | 2024-09-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 6 | M1 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 6 | M1 |  | 2025-02-22
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 6 | M1 |  | 2025-02-22
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 6 | M2 |  | 2024-10-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 6 | M2 |  | 2025-02-10
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 6 | M2 |  | 2025-02-22
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 6 | M2 |  | 2025-02-22
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 6 | M3 |  | 2024-09-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 6 | M3 |  | 2025-02-07
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 6 | M3 |  | 2025-02-22
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 6 | M3 |  | 2025-02-22
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 7 | M1 |  | 2024-10-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 7 | M1 |  | 2025-02-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 7 | M1 |  | 2025-03-01
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 7 | M1 |  | 2025-03-01
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 7 | M2 |  | 2024-10-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 7 | M2 |  | 2025-02-12
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 7 | M2 |  | 2025-02-26
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 7 | M2 |  | 2025-02-26
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 7 | M3 |  | 2024-10-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 7 | M3 |  | 2025-02-12
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 7 | M3 |  | 2025-02-28
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 7 | M3 |  | 2025-02-28
Fabrication | PPVC | Casting |  |  |  | 5 |  | 8 | 7 | M4 |  | 2024-10-25
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 8 | 7 | M4 |  | 2025-02-10
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 8 | 7 | M4 |  | 2025-02-22
Fabrication | PPVC | Installation |  |  |  | 5 |  | 8 | 7 | M4 |  | 2025-02-22
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 1 | M1 |  | 2024-09-21
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 1 | M1 |  | 2025-02-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 1 | M1 |  | 2025-02-12
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 1 | M1 |  | 2025-02-12
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 1 | M2 |  | 2024-09-25
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 1 | M2 |  | 2025-02-05
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 1 | M2 |  | 2025-02-13
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 1 | M2 |  | 2025-02-13
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 1 | M3 |  | 2024-10-01
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 1 | M3 |  | 2025-02-05
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 1 | M3 |  | 2025-02-13
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 1 | M3 |  | 2025-02-13
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 1 | M4 |  | 2024-10-15
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 1 | M4 |  | 2025-02-15
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 1 | M4 |  | 2025-02-15
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 1 | M4 |  | 2025-02-15
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 2 | M1 |  | 2024-08-16
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 2 | M1 |  | 2025-02-04
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 2 | M1 |  | 2025-02-15
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 2 | M1 |  | 2025-02-15
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 2 | M2 |  | 2024-09-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 2 | M2 |  | 2025-02-05
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 2 | M2 |  | 2025-02-17
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 2 | M2 |  | 2025-02-17
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 2 | M3 |  | 2024-08-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 2 | M3 |  | 2025-02-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 2 | M3 |  | 2025-02-17
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 2 | M3 |  | 2025-02-17
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 3 | M1 |  | 2024-08-26
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 3 | M1 |  | 2025-02-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 3 | M1 |  | 2025-02-18
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 3 | M1 |  | 2025-02-18
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 3 | M2 |  | 2024-09-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 3 | M2 |  | 2025-02-07
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 3 | M2 |  | 2025-02-18
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 3 | M2 |  | 2025-02-18
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 3 | M3 |  | 2024-09-20
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 3 | M3 |  | 2025-02-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 3 | M3 |  | 2025-02-18
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 3 | M3 |  | 2025-02-18
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 3 | M4 |  | 2024-08-28
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 3 | M4 |  | 2025-02-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 3 | M4 |  | 2025-02-18
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 3 | M4 |  | 2025-02-18
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 3 | M5 |  | 2024-09-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 3 | M5 |  | 2025-02-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 3 | M5 |  | 2025-02-19
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 3 | M5 |  | 2025-02-19
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 4 | M1 |  | 2024-10-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 4 | M1 |  | 2025-01-25
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 4 | M1 |  | 2025-02-08
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 4 | M1 |  | 2025-02-08
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 4 | M2 |  | 2024-10-12
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 4 | M2 |  | 2025-02-04
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 4 | M2 |  | 2025-02-08
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 4 | M2 |  | 2025-02-08
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 4 | M3 |  | 2024-10-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 4 | M3 |  | 2025-01-25
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 4 | M3 |  | 2025-02-08
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 4 | M3 |  | 2025-02-08
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 4 | M4 |  | 2024-10-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 4 | M4 |  | 2025-02-05
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 4 | M4 |  | 2025-02-08
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 4 | M4 |  | 2025-02-08
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 5 | M1 |  | 2024-09-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 5 | M1 |  | 2025-02-04
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 5 | M1 |  | 2025-02-08
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 5 | M1 |  | 2025-02-08
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 5 | M2 |  | 2024-12-02
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 5 | M2 |  | 2025-02-04
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 5 | M2 |  | 2025-02-10
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 5 | M2 |  | 2025-02-10
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 5 | M3 |  | 2024-09-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 5 | M3 |  | 2025-02-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 5 | M3 |  | 2025-02-11
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 5 | M3 |  | 2025-02-11
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 6 | M1 |  | 2024-09-13
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 6 | M1 |  | 2025-01-25
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 6 | M1 |  | 2025-02-12
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 6 | M1 |  | 2025-02-12
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 6 | M2 |  | 2024-10-01
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 6 | M2 |  | 2025-01-27
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 6 | M2 |  | 2025-02-10
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 6 | M2 |  | 2025-02-10
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 6 | M3 |  | 2024-09-21
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 6 | M3 |  | 2025-01-23
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 6 | M3 |  | 2025-02-10
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 6 | M3 |  | 2025-02-10
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 7 | M1 |  | 2024-10-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 7 | M1 |  | 2025-01-25
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 7 | M1 |  | 2025-02-19
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 7 | M1 |  | 2025-02-19
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 7 | M2 |  | 2024-10-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 7 | M2 |  | 2025-02-05
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 7 | M2 |  | 2025-02-14
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 7 | M2 |  | 2025-02-14
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 7 | M3 |  | 2024-10-19
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 7 | M3 |  | 2025-02-04
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 7 | M3 |  | 2025-02-14
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 7 | M3 |  | 2025-02-14
Fabrication | PPVC | Casting |  |  |  | 5 |  | 7 | 7 | M4 |  | 2024-10-22
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 7 | 7 | M4 |  | 2025-02-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 7 | 7 | M4 |  | 2025-02-14
Fabrication | PPVC | Installation |  |  |  | 5 |  | 7 | 7 | M4 |  | 2025-02-14
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 1 | M1 |  | 2024-09-19
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 1 | M1 |  | 2025-01-23
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 1 | M1 |  | 2025-02-04
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 1 | M1 |  | 2025-02-04
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 1 | M2 |  | 2024-09-21
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 1 | M2 |  | 2025-02-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 1 | M2 |  | 2025-02-05
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 1 | M2 |  | 2025-02-05
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 1 | M3 |  | 2024-09-27
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 1 | M3 |  | 2025-02-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 1 | M3 |  | 2025-02-04
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 1 | M3 |  | 2025-02-04
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 1 | M4 |  | 2024-10-12
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 1 | M4 |  | 2025-02-04
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 1 | M4 |  | 2025-02-04
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 1 | M4 |  | 2025-02-04
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 2 | M1 |  | 2024-08-13
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 2 | M1 |  | 2025-01-15
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 2 | M1 |  | 2025-02-05
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 2 | M1 |  | 2025-02-05
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 2 | M2 |  | 2024-08-26
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 2 | M2 |  | 2025-01-15
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 2 | M2 |  | 2025-02-05
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 2 | M2 |  | 2025-02-05
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 2 | M3 |  | 2024-08-15
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 2 | M3 |  | 2025-01-15
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 2 | M3 |  | 2025-02-06
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 2 | M3 |  | 2025-02-06
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 3 | M1 |  | 2024-08-19
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 3 | M1 |  | 2025-01-17
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 3 | M1 |  | 2025-02-06
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 3 | M1 |  | 2025-02-06
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 3 | M2 |  | 2024-09-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 3 | M2 |  | 2025-01-18
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 3 | M2 |  | 2025-02-06
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 3 | M2 |  | 2025-02-06
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 3 | M3 |  | 2024-09-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 3 | M3 |  | 2025-01-17
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 3 | M3 |  | 2025-02-06
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 3 | M3 |  | 2025-02-06
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 3 | M4 |  | 2024-08-26
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 3 | M4 |  | 2025-01-17
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 3 | M4 |  | 2025-05-07
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 3 | M4 |  | 2025-05-07
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 3 | M5 |  | 2024-09-09
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 3 | M5 |  | 2025-01-16
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 3 | M5 |  | 2025-05-07
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 3 | M5 |  | 2025-05-07
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 4 | M1 |  | 2024-10-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 4 | M1 |  | 2024-12-12
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 4 | M1 |  | 2025-01-27
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 4 | M1 |  | 2025-01-27
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 4 | M2 |  | 2024-10-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 4 | M2 |  | 2024-12-12
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 4 | M2 |  | 2025-01-27
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 4 | M2 |  | 2025-01-27
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 4 | M3 |  | 2024-10-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 4 | M3 |  | 2024-12-13
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 4 | M3 |  | 2025-01-27
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 4 | M3 |  | 2025-01-27
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 4 | M4 |  | 2024-10-01
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 4 | M4 |  | 2024-12-13
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 4 | M4 |  | 2025-02-03
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 4 | M4 |  | 2025-02-03
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 5 | M1 |  | 2024-08-30
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 5 | M1 |  | 2025-01-14
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 5 | M1 |  | 2025-02-03
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 5 | M1 |  | 2025-02-03
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 5 | M2 |  | 2024-09-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 5 | M2 |  | 2025-01-14
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 5 | M2 |  | 2025-02-03
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 5 | M2 |  | 2025-02-03
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 5 | M3 |  | 2024-12-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 5 | M3 |  | 2025-01-14
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 5 | M3 |  | 2025-02-03
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 5 | M3 |  | 2025-02-03
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 6 | M1 |  | 2024-09-11
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 6 | M1 |  | 2025-01-25
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 6 | M1 |  | 2025-02-04
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 6 | M1 |  | 2025-02-04
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 6 | M2 |  | 2024-10-23
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 6 | M2 |  | 2025-01-25
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 6 | M2 |  | 2025-02-04
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 6 | M2 |  | 2025-02-04
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 6 | M3 |  | 2024-09-19
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 6 | M3 |  | 2025-01-23
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 6 | M3 |  | 2025-02-03
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 6 | M3 |  | 2025-02-03
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 7 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 7 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 7 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 6 | 7 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 6 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 6 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 6 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 1 | M1 |  | 2024-09-16
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 1 | M1 |  | 2024-11-22
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 1 | M1 |  | 2025-01-20
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 1 | M1 |  | 2025-01-20
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 1 | M2 |  | 2024-09-18
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 1 | M2 |  | 2024-11-22
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 1 | M2 |  | 2025-01-20
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 1 | M2 |  | 2025-01-20
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 1 | M3 |  | 2024-09-23
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 1 | M3 |  | 2024-11-22
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 1 | M3 |  | 2025-01-21
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 1 | M3 |  | 2025-01-21
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 1 | M4 |  | 2024-10-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 1 | M4 |  | 2024-11-22
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 1 | M4 |  | 2025-01-21
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 1 | M4 |  | 2025-01-21
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 2 | M1 |  | 2024-08-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 2 | M1 |  | 2024-08-17
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 2 | M1 |  | 2025-01-23
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 2 | M1 |  | 2025-01-23
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 2 | M2 |  | 2024-09-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 2 | M2 |  | 2024-11-25
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 2 | M2 |  | 2025-01-23
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 2 | M2 |  | 2025-01-23
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 2 | M3 |  | 2024-08-13
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 2 | M3 |  | 2024-11-25
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 2 | M3 |  | 2025-01-23
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 2 | M3 |  | 2025-01-23
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 3 | M1 |  | 2024-08-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 3 | M1 |  | 2024-12-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 3 | M1 |  | 2025-01-23
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 3 | M1 |  | 2025-01-23
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 3 | M2 |  | 2024-09-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 3 | M2 |  | 2024-12-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 3 | M2 |  | 2025-01-23
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 3 | M2 |  | 2025-01-23
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 3 | M3 |  | 2024-09-07
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 3 | M3 |  | 2024-12-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 3 | M3 |  | 2025-01-23
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 3 | M3 |  | 2025-01-23
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 3 | M4 |  | 2024-08-20
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 3 | M4 |  | 2024-12-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 3 | M4 |  | 2025-01-24
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 3 | M4 |  | 2025-01-24
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 3 | M5 |  | 2024-09-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 3 | M5 |  | 2024-12-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 3 | M5 |  | 2025-01-24
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 3 | M5 |  | 2025-01-24
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 4 | M1 |  | 2024-10-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 4 | M1 |  | 2024-11-30
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 4 | M1 |  | 2025-01-18
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 4 | M1 |  | 2025-01-18
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 4 | M2 |  | 2024-10-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 4 | M2 |  | 2024-12-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 4 | M2 |  | 2025-01-18
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 4 | M2 |  | 2025-01-18
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 4 | M3 |  | 2024-10-02
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 4 | M3 |  | 2024-12-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 4 | M3 |  | 2025-01-18
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 4 | M3 |  | 2025-01-18
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 4 | M4 |  | 2024-09-28
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 4 | M4 |  | 2024-12-03
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 4 | M4 |  | 2025-01-18
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 4 | M4 |  | 2025-01-18
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 5 | M1 |  | 2024-08-27
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 5 | M1 |  | 2024-11-30
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 5 | M1 |  | 2025-01-18
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 5 | M1 |  | 2025-01-18
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 5 | M2 |  | 2024-09-12
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 5 | M2 |  | 2024-11-30
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 5 | M2 |  | 2025-01-18
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 5 | M2 |  | 2025-01-18
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 5 | M3 |  | 2024-11-29
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 5 | M3 |  | 2024-12-06
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 5 | M3 |  | 2025-01-20
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 5 | M3 |  | 2025-01-20
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 6 | M1 |  | 2024-09-06
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 6 | M1 |  | 2024-11-29
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 6 | M1 |  | 2025-01-20
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 6 | M1 |  | 2025-01-20
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 6 | M2 |  | 2024-10-04
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 6 | M2 |  | 2024-11-29
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 6 | M2 |  | 2025-01-20
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 6 | M2 |  | 2025-01-20
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 6 | M3 |  | 2024-09-16
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 6 | M3 |  | 2024-11-29
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 6 | M3 |  | 2025-01-20
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 6 | M3 |  | 2025-01-20
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 7 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 7 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 7 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 5 | 7 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 5 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 5 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 5 | 7 | M4
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 1 | M1 |  | 2024-09-13
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 1 | M1 |  | 2024-10-30
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 1 | M1 |  | 2025-01-11
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 1 | M1 |  | 2025-01-11
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 1 | M2 |  | 2024-09-14
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 1 | M2 |  | 2024-10-30
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 1 | M2 |  | 2025-01-11
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 1 | M2 |  | 2025-01-11
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 1 | M3 |  | 2024-09-19
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 1 | M3 |  | 2024-10-30
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 1 | M3 |  | 2025-01-11
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 1 | M3 |  | 2025-01-11
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 1 | M4 |  | 2024-10-08
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 1 | M4 |  | 2024-10-30
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 1 | M4 |  | 2025-01-13
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 1 | M4 |  | 2025-01-13
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 2 | M1 |  | 2024-08-05
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 2 | M1 |  | 2024-08-17
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 2 | M1 |  | 2025-01-13
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 2 | M1 |  | 2025-01-13
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 2 | M2 |  | 2024-08-29
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 2 | M2 |  | 2024-09-05
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 2 | M2 |  | 2025-01-13
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 2 | M2 |  | 2025-01-13
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 2 | M3 |  | 2024-08-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 2 | M3 |  | 2024-08-21
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 2 | M3 |  | 2025-01-13
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 2 | M3 |  | 2025-01-13
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 3 | M1 |  | 2024-08-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 3 | M1 |  | 2024-08-23
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 3 | M1 |  | 2025-01-13
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 3 | M1 |  | 2025-01-13
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 3 | M2 |  | 2024-08-30
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 3 | M2 |  | 2024-09-05
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 3 | M2 |  | 2025-01-13
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 3 | M2 |  | 2025-01-13
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 3 | M3 |  | 2024-09-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 3 | M3 |  | 2024-09-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 3 | M3 |  | 2025-01-14
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 3 | M3 |  | 2025-01-14
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 3 | M4 |  | 2024-08-15
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 3 | M4 |  | 2024-08-29
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 3 | M4 |  | 2025-01-14
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 3 | M4 |  | 2025-01-14
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 3 | M5 |  | 2024-09-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 3 | M5 |  | 2024-09-07
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 3 | M5 |  | 2025-01-14
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 3 | M5 |  | 2025-01-14
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 4 | M1 |  | 2024-09-30
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 4 | M1 |  | 2024-10-24
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 4 | M1 |  | 2025-01-02
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 4 | M1 |  | 2025-01-09
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 4 | M2 |  | 2024-09-30
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 4 | M2 |  | 2024-10-24
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 4 | M2 |  | 2025-01-02
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 4 | M2 |  | 2025-01-09
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 4 | M3 |  | 2024-09-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 4 | M3 |  | 2024-10-24
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 4 | M3 |  | 2025-01-02
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 4 | M3 |  | 2025-01-09
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 4 | M4 |  | 2024-09-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 4 | M4 |  | 2024-10-24
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 4 | M4 |  | 2025-01-02
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 4 | M4 |  | 2025-01-09
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 5 | M1 |  | 2024-08-24
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 5 | M1 |  | 2024-11-05
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 5 | M1 |  | 2025-01-10
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 5 | M1 |  | 2025-01-10
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 5 | M2 |  | 2024-09-10
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 5 | M2 |  | 2024-11-05
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 5 | M2 |  | 2025-01-10
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 5 | M2 |  | 2025-01-10
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 5 | M3 |  | 2024-08-29
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 5 | M3 |  | 2024-11-05
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 5 | M3 |  | 2025-01-10
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 5 | M3 |  | 2025-01-10
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 6 | M1 |  | 2024-09-03
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 6 | M1 |  | 2024-11-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 6 | M1 |  | 2025-01-11
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 6 | M1 |  | 2025-01-11
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 6 | M2 |  | 2024-09-26
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 6 | M2 |  | 2024-11-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 6 | M2 |  | 2025-01-11
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 6 | M2 |  | 2025-01-11
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 6 | M3 |  | 2024-09-12
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 6 | M3 |  | 2024-11-08
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 6 | M3 |  | 2025-01-11
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 6 | M3 |  | 2025-01-11
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 7 | M1
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 7 | M1
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 7 | M1
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 7 | M1
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 7 | M2
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 7 | M2
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 7 | M2
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 7 | M2
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 7 | M3
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 7 | M3
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 7 | M3
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 7 | M3
Fabrication | PPVC | Casting |  |  |  | 5 |  | 4 | 7 | M4
Fabrication | PPVC | Delivery |  |  |  | 5 |  | 4 | 7 | M4
Fabrication | PPVC | Fit Out |  |  |  | 5 |  | 4 | 7 | M4
Fabrication | PPVC | Installation |  |  |  | 5 |  | 4 | 7 | M4